## Overview
QBWA Mapping Guide - Overview and Tips
This mapping guide is the key to defining the "business rules" that QBWA will use when transferring financial documents from Wild Apricot to Quickbooks. Fill out as much of the spreadsheet as you can. Reach out to your NPC focal for any clarifications or questions. Once the spreadsheeet is completed, you will meet with your NPC focal on a Zoom call to review together. It will be helpful to have people on the call that understand both the Wild Apricot setup for your organization as well as the Quickbooks setup.
High Level Phases to Setup QBWA:
| Project Prep | Completing this Mapping Guide; establishing connections to your systems
| Config Prep | Reviewing data; making recommendations for config and for changes to WildApricot or Quickbooks
| Installation | NPC Install and Configuration
| Testing | Test runs for defined dates
| Go Live & Transition to Support | Initiate auto-scheduled runs
Overview of this Mapping Guide
1 | The initial Sheets describe information about your organization. (Interview, General, Connections)
2 | The Config Recommendations and Test Tracker Sheets are used by your NPC focal to document recommendations and track testing progress.
3 | The “Job Scheduling” Sheet is to set up how often and on what days, you would like the automation to run, for your QB. If you are not sure about the schedule, this can be filled at a later time. See the "EXAMPLE: Scheduled" sheet to understand some example setups.
4 | The "Contact-Customer Config" sheet defines the fields used in Wild Apricot for Contact information and the format you use for Customer names inside Quickbooks.
5 | The primary "business rule mapping" sheets are: Invoice, Payment, Donation and Sales Tax. Fill out the sheets that correspond to the transactions that are in scope for your organization.
Tips for Using and Navigating the Mapping Guide:
1 | On most of the sheets, there are plus and minus symbols ( + / - ) on the far left. These will expand and collapse the sections. This feature can be used to help focus on one section at a time.
2 | Many of the detailed mapping sheets are organized in three sections. An information section (at the top), business mapping rules section in the middle, and example section (at the bottom), that further explains what is required.
3 | The "Downloaded QBO..." sheets are only for Quickbooks Online. Once a connection is established to your systems, your NPC focal will populate this tabs for you to assist with the identifcation of the proper QBO ID numbers for the business rules.
4 |  | On the lower left, use the "stacked burger" shaped button to show a list of the sheets. It may be easier to navigate to a sheet using this button rather than scrolling left and right.
Notes about Quickbooks Objects:
The accounts, products (inventory list items), and classes referenced on each sheet are required as listed. These are based on limitations in Quickbooks for creating each transaction type or to support the business rule mappings inside QBWA. Contact your NPC Focal for questions.

## Interview v.7
QBWA Mapping Guide - Preliminary Interview
This workbook is used to perform initial configuration of a QBWA installation for a new client. Go through each tab that is in scope and enter the necessary mapping details from Wild Apricot and Quickbooks. This sheet includes general questions to help understand the scope of QBWA implementation. Actual mappings are on different sheets.
Company Name
Goals for using QBWA: |  | example: reduce data entry
example: better revenue reporting inside Quickbooks
In scope areas: (does not drive configuration; only used to focus discussion on correct configuration areas)
| Membership Invoices | Choose from drop-down: In Scope / Not Used
| Invoice Extra Cost Fields | Choose from drop-down: In Scope / Not Used
| Event Invoices | Choose from drop-down: In Scope / Not Used
| Online Store Invoices | Choose from drop-down: In Scope / Not Used
| Manual Item Invoices | Choose from drop-down: In Scope / Not Used
| Payments | Choose from drop-down: In Scope / Not Used
| Donations | Choose from drop-down: In Scope / Not Used
Company Participants to setup QBWA:
Person with knowledge of Wild Apricot setup |  | name and email
Person with knowledge of Quickbooks setup |  | name and email
Person with access to update domain/website DNS settings |  | name and email (DNS updates are used for "Mailgun" email notification utility)
General Wild Apricot questions:
How many years has Wild Apricot been used?
How many active, paid Membership Levels are used?
Approximately how many members do you have?
How many events per year do you typically have?
How many Event Tags are used?
Are different Donation campaigns/funds used?
Do you regularly use Manual Invoices?
Do you regularly edit past invoices?
Do you use Affinipay (WildApricot Payments)? or a different payment gateway?
Do you record manual payments inside WA when you receive checks or cash?
Do you use Sales Taxes inside Wild Apricot?
General Quickbooks questions:
How many years has Quickbooks been used?
Do you use Quickbooks Desktop or Online?
Which specific Quickbooks version? (country)
Do you use "cash accounting" or "accrual accounting"?
Do you use Sales Taxes in Quickbooks?
How many active Quickbooks Income Accounts are used?
Do you use Quickbooks Products (Sales Inventory List Items)?
Do you use Quickbooks Classes?
Do you add/update your accounts, classes, and/or products more than annually?
Are Wild Apricot members/donors already inside Quickbooks as Customers?
Other install project questions:
Do you have a date (or milestone) by which you want the install to be completed?
Will you need to "load" historic WildApricot transactions into Quickbooks? |  | how many months back?

## General
QBWA Mapping Guide - General
This section includes the general sections of the QBWA configuration. Notes and examples are in blue text.
WA Org Name |  |  | Free Text. Max 41 characters.
WA Config Record Name |  | n/a (NPC focal will define) | n/a for initial; consider naming conventions such as <Customer Name> - <MASTER - USE>
Org Primary Timezone (matching Wild Apricot time zone) |  |  | must exactly match the "TZ database name" from the linked wiki page (e.g. America/Chicago)
Config Last Updated |  | n/a (NPC focal will define) | n/a for initial; suggest changing date manually for each major changee
QB Version Info
| QB Country |  | CAD (Canada), US (United States)
| QB Platform |  | Desktop, Online
| QBO Root URL | http://app.company.qbo.intuit.com | Quickbooks Online ONLY
QBWA Version Info
| NPC License Key |  | n/a; NPC focal will provide when installed
| QBWA Invoice Core Scenario Version |  | n/a; NPC focal will provide when installed
| QBWA Payment Core Scenario Version |  | n/a; NPC focal will provide when installed
| QBWA Donation Core Scenario Version |  | n/a; NPC focal will provide when installed
| QBWA Transaction Loader Scenario Version (QBD or QBO) |  | n/a; NPC focal will provide when installed
Output File Location (Online storage service for Quickbooks Desktop only; use +/- to expand/collapse)
| Online Storage Service | box | free text (e.g. box, OneDrive, DropBox, GoogleDrive)
Invoice | Invoice Folder Path | /<company>/QBWA-Invoices | For "box" this is only a reference. Folder must be slected inside the scenario.
Invoice | Success Invoice Filename Format | QBWA_Invoice_IIF_{DateTime}
Payment | Payment Folder Path | /<company>/QBWA-Payments | For "box" this is only a reference. Folder must be slected inside the scenario.
Payment | Success Payment Filename Format | QBWA_Payment_IIF_{DateTime}
Donation | Donation Folder Path | /<company>/QBWA-Donations | For "box" this is only a reference. Folder must be slected inside the scenario.
Donation | Success Donation Filename Format | QBWA_Donation_IIF_{DateTime}
Notifications Emails ( summary sent by QBWA after each run)
| From Email Address |  | All success and ERROR files will be sent "from" this email (one email address only)
| To: Email Addresses |  | All success and ERROR files will be sent to this email in the TO: field (multiple addreses accepted in configuration)
| Bcc: Email Addresses |  | All success and ERROR files will be sent to this email in the BCC: field (multiple addreses accepted in configuration)

## Connections
QBWA Mapping Guide - Account Connections
To support installation of QBWA, NPC will need your account credentials OR will need to work closely with you to establish connections to these online services. If NPC does this on your behalf, NPC will need your password to create the initial connection.
Make.com: | Create a Make.com account with at least the BASIC subscription level.
| Person (email address) of account owner | owner from your company
| NPC focal (email address) to be invited as ADMIN user | ask your NPC focal for proper email address(es); once confirmed invite these email addresses to your Integromat account as an ADMIN user.
Wild Apricot:
| Person (email address) of admin | for reference only
| API Key for Make.com | reference this linked article for instructions to authorize Make.com. Use read only server access.
Website/Email Domain:
| Website/Email address domain to support notifications | NOTE: QBWA uses "Mailgun" as a utility to send notification emails with information about the SUCCESS or ERROR of a run. Additional DNS settings for the listed website domain are needed to allow "Mailgun" to send these emails on your behalf.
Quickbooks Online: | (ignore for QB Desktop users)
| Person (email address) of admin/accountant that create list items and transactions | NOTE: This workbook has sheets at the end with names beginning with "Example QBO." These can be populated from Integromat to aid in the mapping process for QuickBooks Online. Some of the configurations require the Quickbooks ID for the Accounts, Classes, and Products. These are not easy to find directly within Quickbooks Online. Use the Integormat Scenario "QBWA QBO Mapping Queries - Load QBWA Mapping Master" and connect to this mapping workbook to populate from the client's QBO account.
Storage Service: | (for QB Desktop only; ignore for QB Online users)
| Online Storage Service | free text (e.g. box, OneDrive, DropBox, GoogleDrive)
Person (email address) of admin with permission to create connections, folders, files

## Config Recommendations
This section will be filled out by your NPC focal during the project.
General Observations and Questions
(your NPC focal will fill out this section after reviewing your existing data and business goals)
QBO Classes:
QBO Products:
QBO Deposit Account:
QBO Income Accounts: (relevant)
WA Member Levels:
WA Event "tags":
Configuration Recommendations
(your NPC focal will use this to summarize recommendations for QBWA and for any changes inside WildApricot or Quickbooks)
QBWA Income Config Mapping Summary
| WA Invoice Order Type | Business Rule Mapping | QB Income Account | QB Item Product Name | QB Class
| Membership | DEFAULT (back-up for no matching WA Member Level)
Member Level =
Member Level =
Member Level =
| Event | DEFAULT (back-up for no matching WA event tag)
WA event tag =
WA event tag =
WA event tag =
| Online Store | DEFAULT (no granular mappings possible)
| Manual Invoice (Undefined) | DEFAULT (no granular mappings possible)
| Donation | DEFAULT (back-up for no matching WA Campaign)
Campaign =
Campaign =
Campaign =
Recommended Updates for WildApricot
Recommended Updates for Quickbooks
Creating Income Accounts in QBO
Settings (gear icon - upper right) --> Chart of accounts --> New
1.) Account Type = Revenue
2.) Sub Account Type = <choose from list>
3.) Name
4.) Description (optional)
5.) Save
Creating Products in QBO
Sales (menu left hand side) --> Products and Services --> New
1.). Choose Type: Service or Non-Inventory (Bundles are not supported by QBWA at this time; Inventory may be used, but requires additional Quickbooks maintenance.)
2.) Specify Name
3.) Ensure "I sell this product/service..." is selected.
4.) Choose the appropriate Income account for the Product/Service.
5.) Save
NOTE: Some Quickbooks versions may use terms other than "Sales" on the left hand version
Creating Classes in QBO
Settings (gear icon - upper right) --> All Lists --> Classes --> New
1.) Enter Name
2.) Optional - define as Sub Class to a Parent Class
3.) Save

## Test Tracker
QBWA Test Tracker
This section will be used to track the QBWA testing after installation and configuration. Your NPC focal will work with you to pick WildApricot transactions to test each area of QBWA.
Wild Apricot Order Type | Customer Name | Invoice/Donation Document Number | Invoice/Donation Date | "Type" (e.g. Renewal, Member Level, event tag, campaign, etc.) | Payment Date | Payment ID (from URL inside Wild Apricot) | Test Results | Other Notes
Membership
Event Registration
Online Store
Manual (Undefined)
Donation

## Job Scheduling
QBWA Mapping Guide - Scheduling
Use the "+/-" on the left to collapse/expand sections.
General Information about Scheduling Settings: (use the "+/-" on the left to collapse/expand notes.)
Generally, the "Manual" setting is used during set-up/testing. Most clients use the "Scheduled" setting after initial set-up.
"Manual" run settings: The start date and end date define the period during which transactions will be read from Wild Apricot. If a Document Number is specified, this will be additionally filtered to ONLY process the specific transaction. NOTE: Inside Integromat Config, the DateTime will be shown visually relative to the timezone setting inside Integromat for the user doing the data entry. If the WA time zone is different, adjust the time as appropriate during data entry to account for any time zone differences. In the backend, the proper date-time is stored. Example: If a midnight start time in the Central timezone is desired (12:00 AM) AND the person doing the data entry has a Pacific timezone setting, the data entry person should enter 10:00 PM on the previous day to account for the 2 hour difference.
"Scheduled" run settings: The Time Period and Number of Periods are used to define how often QBWA will run and over what timer period transactions will be read from Wild Apricot. e.g. using "Weekly" and "2" will cause QBWA to run every 2 weeks. When QBWA runs, it will read the transactions from the previous 2 week period, not including the day that QBWA runs. e.g. using "Monthly" and "1" will cause QBWA to run every 1 month. When QBWA runs, it will read the transactions from the previous 1 month period, not including the day that QBWA runs. The "Day of Week" and the "Day of Month" settings tell QBWA which days the run should start. If the Daily setting is used, QBWA will run every day. e.g. using "Mon" will cause QBWA to run on Mondays each week (or every 2 weeks if the number of periods is set to 2). e.g. using "9" will cause QBWA to run on the 9th day of each month. See the "EXAMPLE: Scheduled" sheet for more detailed example settings.
Invoice Scheduling (use the "+/-" on the left to collapse/expand section.)
Invoice Enabled |  | defaults to "true"
Invoice Job Scheduling Type |  | Manual or Scheduled
Invoice "Manual" Run Schedule Settings
| Manual Start Date | If Scheduling Type = Manual, this date is used as start date for Invoices (YYYY-MM-DD HH:mm --> system automatically assumes 00 seconds)
| Manual End Date | If Scheduling Type = Manual, this date is used as end date for Invoices (YYYY-MM-DD HH:mm --> system automatically assumes 59 seconds)
| Manual Invoice Doc Number | The customer visible Invoice document number from Wild Apricot. This document must fall within the start and end date above.
Invoice Auto Run "Scheduled" Settings
| Time Period for Each Run | Daily, Weekly, Monthly
| Number of Time Periods | 1 | e.g. use 2 if it should run every 2 weeks [use 1 for Daily]
| Weekly: Day of Week to Start Run | Mon | 3 letter day of week [leave blank for Daily or Monthly]
| Monthly: Day of Month to Start Run | 9 | number representing the day of the month
| Start Time for Run (reference only) | 0:00 | must be offset from the start time from the other transactions; should be before Payment scenario start time.
Payment Scheduling (use the "+/-" on the left to collapse/expand section.)
Payment Enabled |  | defaults to "true"
Payment Job Scheduling Type |  | Manual or Scheduled
Payment "Manual" Run Schedule Settings
| Manual Start Date | If Scheduling Type = Manual, this date is used as start date for Payments (YYYY-MM-DD HH:mm --> system automatically assumes 00 seconds)
| Manual End Date | If Scheduling Type = Manual, this date is used as end date for Payments (YYYY-MM-DD HH:mm --> system automatically assumes 59 seconds)
| Manual Payment ID Number | This document must fall within the start and end date above.
NOTE: There is no customer visible document number in the UI. This uses the backend Payment ID inside Wild Apricot that is visible in the Wild Apricot Payment URL.
Payment Auto Run "Scheduled" Settings
| Time Period for Each Run | Daily, Weekly, Monthly
| Number of Time Periods | 1 | e.g. use 2 if it should run every 2 weeks [use 1 for Daily]
| Weekly: Day of Week to Start Run | Mon | 3 letter day of week [leave blank for Daily or Monthly]
| Monthly: Day of Month to Start Run | 9 | number representing the day of the month
| Start Time for Run (reference only) | 0:20 | must be offset from the start time from the other transactions; should be after Invoice scenario start time.
Donation Scheduling (use the "+/-" on the left to collapse/expand section.)
Donation Enabled |  | defaults to "true"
Donation Job Scheduling Type |  | Manual or Scheduled
Donation "Manual" Run Schedule Settings
| Manual Start Date | If Scheduling Type = Manual, this date is used as start date for Donations (YYYY-MM-DD HH:mm --> system automatically assumes 00 seconds)
| Manual End Date | If Scheduling Type = Manual, this date is used as end date for Donations (YYYY-MM-DD HH:mm --> system automatically assumes 59 seconds)
| Manual Donation Doc Number | The customer visible Donation document number from Wild Apricot. This document must fall within the start and end date above.
Donation Auto Run "Scheduled" Settings
| Time Period for Each Run | Daily, Weekly, Monthly
| Number of Time Periods | 1 | e.g. use 2 if it should run every 2 weeks [use 1 for Daily]
| Weekly: Day of Week to Start Run | Mon | 3 letter day of week [leave blank for Daily or Monthly]
| Monthly: Day of Month to Start Run | 9 | number representing the day of the month
| Start Time for Run (reference only) | 0:40 | must be offset from the start time from the other transactions

## Contact-Customer Info
QBWA Mapping Guide - Customer Config
These fields are used to confirm how Customer Contact information is shown on the header of the Quickbooks Transactions
Wild Apricot Contact Field Names |  | Enter the Label of the corresponding field inside Wild Apricot. Not all companies use the same labels.
| User ID |  | e.g. User ID
| First Name |  | e.g. First Name
| Last Name |  | e.g. Last Name
| Email |  | e.g. Email
| Phone |  | e.g. Phone
| Organization |  | e.g. Organization
| Street Address 1 |  | e.g. Street
Street Address 2
| City |  | e.g. City
| Province |  | e.g. State
| Postal Code |  | e.g. Zip Code
| Country |  | e.g. Country
Quickbooks Display Name Format |  |  | e.g. "First Name Last Name", "Last Name, First Name", "Organization Name"
(for both Quickbooks Online and Desktop) |  |  | Supported tokens: {Organization}, {User Id}, {Display Name}, {Email}, {Full Name}
NOTE: Quickbooks uses "Display Name" as the unique identifier of a Customer to prevent dupplicates. The same name cannot be duplicated across Customers, Vendors, or Employees inside Quickbooks.
QB Desktop Billing Address Format |  | (ignore for Quickbooks Online)
|  | Each field has a Max of 41 characters | Use these fields to describe how Wild Apricot Contact info is used to define the QB Billing Address on invoices. (does not update the Customer record inside QB Desktop)
| Line 1: |  | Supported tokens: {Organization}, {Display Name}, {Full Name}, {User Id}, {Email} (scenario can be customized to use other tokens)
| Line 2: |  | Supported tokens: {Organization}, {Display Name}, {Full Name}, {User Id}, {Email} (scenario can be customized to use other tokens)
| Line 3: | {Street Address 1} | Supported tokens: {Strret Address 1}, {Street Address 2}, {City}, {Province}, {Postal Code}, {Country} (scenario can be customized to use other tokens)
| Line 4: | {Street Address 2} | Supported tokens: {Strret Address 1}, {Street Address 2}, {City}, {Province}, {Postal Code}, {Country} (scenario can be customized to use other tokens)
| Line 5: | {City}, {Province} {Postal Code} | Supported tokens: {Strret Address 1}, {Street Address 2}, {City}, {Province}, {Postal Code}, {Country} (scenario can be customized to use other tokens)

## Invoice Config
QBWA Mapping Guide - Invoice Mapping Config
Use the "+/-" on the left to collapse/expand sections.
NOTES for Invoice Configuration:
| General | This sheet is focused on the mapping of Invoice documents. Each section is focused on a different "Invoice Order Type" from Wild Apricot. The listed mappings apply to all line items on an invoice. Each "Invoice Order Type" has a Default set of Quickbooks mappings.
| Alternate Mappings | Additionally, some of the sections allow for an Alternative Mapping Filter that can be used to provide alternate Quickbooks mappings for an Invoice that uses that filter. (e.g. A "Membership Level Name" for a Membership Invoice) These mappings also apply to all ine items on the invoice.
| Extra Cost Field Line Item Exceptions (General) | The last section defines invoice line item exception mappings using Wild Apricot ExtraCost fields. As an example, an invoice line item for a "special new membership fee" can be mapped to a different Quickbooks income account than the income account used for the other line items on the invoice. Without Extra Cost Line Item mappings, all lines from an Invoice will be mapped to the same Accounts, Products, Classes, etc.
| Extra Cost Field Line Item Exceptions (Supported Variations) | Summarizing the variations of Extra Cost fields that WA allows: 1)Extra Charge Calculation 2)Radio Button selection with Charge 3) Multiple Choice selection with Charge NOTE: These types of fields may be used for memberships or for event registration invoices. QBWA reads the text for a line item and looks for these fields being used. QBWA logic supports these variations of mappings for Invoice Line Item Exceptions: 1) Extra Charge Calculation --> single QBWA mapping row per field name only 2) Radio Button selection with Charge --> single mapping per field name only (e.g. "T-shirt choice" ) 3) Radio Button selection with Charge --> single mapping per field name and single selection combo (e.g. "T-shirt choice - Old Shirt" or "T-shirt choice - New Shirt", where "Old Shirt" and "New Shirt" are options within the "T-shirt choice" field.) 4) Multiple Choice selection with Charge --> single QBWA mapping per field name only NOTE: A combo mapping is not supported for Multiple Choice Extra Charge fields. NOTE2: QBWA must read the configured EC mappings for a client and iterate through each, searching for a match on every invoice line item. For clients with many EC mappings and line items, this can substantially increase the number of Make.com operations consumed.
| Definitions | Receivables Account: account where money due from a customer is posted in Quickbooks. Item Product: products or services sold to a customer. (Quickbooks can use this to define default accounts, pricing, etc. for an item. Income Account: account where revenue is posted from sales to customers. Class: Quickbooks allows Classes to be defined for transactions for reporting purposes. Deposit-To Account: an account that holds actual funds received (e.g. undeposited funds OR a specific bank account)
| Filling out the fields | Use the yellow fields for mapping. Values must match Wild Apricot or Quickbooks exactly. --QB Desktop: Ignore columns that indicate QBO only --QB Online: ID numbers are required. Text account/product/class names are for reference only for QBO. --If using sub accounts/classes, specify the full string with the colon between levels. (e.g. Membership Income:Membership Fees) Refer to Configuration Guide for more details.
QB Receivables Account for Invoices:
AR Account Name:
AR Account ID (QBO only):
WA Invoice Order Type: Membership Application (new members) [use +/- to expand collapse sections]
|  |  | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | WA Filter for Alternate Mapping (Membership Level) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | MembershipApplication | n/a (default mapping)
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
ALTERNATE | MembershipApplication
* insert additional ALTERNATE rows if needed | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Order Type: Membership Renewal [use +/- to expand collapse sections]
|  |  | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | WA Filter for Alternate Mapping (Membership Level) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | MembershipRenewal | n/a (default mapping)
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
ALTERNATE | MembershipRenewal
* insert additional ALTERNATE rows if needed | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Order Type: Membership Level Change [use +/- to expand collapse sections]
|  |  | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | WA Filter for Alternate Mapping (Membership Level) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | MembershipLevelChange | n/a (default mapping)
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
ALTERNATE | MembershipLevelChange
* insert additional ALTERNATE rows if needed | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Order Type: Event Registration (tickets) [use +/- to expand collapse sections]
|  |  | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | WA Filter for Alternate Mapping (Event Tag) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | EventRegistration | n/a (default mapping)
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
ALTERNATE | EventRegistration
* insert additional ALTERNATE rows if needed | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Order Type: Online Store (products sold) [use +/- to expand collapse sections]
|  |  | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | WA Filter for Alternate Mapping (Product Tag) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | Online Store | n/a (default mapping)
* COMING SOON - alternate mappings for Online Store invoices based on Product Tags. | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Order Type: Undefined (manual invoice) [use +/- to expand collapse sections]
Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | n/a (default mapping) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | Undefined | n/a (default mapping)
* no filter available to provide alternate mappings for manually created invoices | [7 empty] | Optional: Allows a Payment to be deposited to this account if the linked Invoice is found and mapped.
WA Invoice Line Item Exceptions: using Extra Cost fields [use +/- to expand collapse sections]
| WA Type | WA Filter for Line Item Alternate Mapping (Extra Cost Field/Choice Mapping) | QB Item Product (Inventory List Item) | QB Item Product ID (QBO only) | QB Income Account | QB Class | QB Class ID (QBO only)
ExtraCost
ExtraCost
ExtraCost
ExtraCost
ExtraCost
ExtraCost
ExtraCost
* insert additional EXTRA COST rows if needed
EXAMPLE: Membership Invoice Mapping |  |  | [use +/- to expand collapse sections]
[5 empty] | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | QB Receivables Account | QB Receivables Account ID (QBO only) | Filter for Alternate Mapping (Membership Level) | QB Default Item Product (Inventory List Item) | QB Default Item Product ID (QBO only) | QB Default Income Account | QB Default Class | QB Default Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | MembershipApplication | Accounts Receivable | 84 | n/a (default mapping) | Memberships | 19 | Membership Fees | Membership | 500000012345 | Undeposited Funds | 4
ALTERNATE | MembershipApplication | n/a for alternate | n/a for alternate | Professional | Memberships:Professional | 20 | Membership Fees:Professional | Membership | 500000012345 | Undeposited Funds | 4
ALTERNATE | MembershipApplication | n/a for alternate | n/a for alternate | Student | Memberships:Student | 21 | Membership Fees:Other | Membership | 500000012345 | Undeposited Funds | 4
EXAMPLE: Event Registration Invoice Mapping |  |  | [use +/- to expand collapse sections]
[5 empty] | <------------------------ DEFAULT mapping is used for invoice if an Alternate mapping is not identified. ---------------------------> |  |  |  |  | Only used if Payments in scope (optional)
DEFAULT or ALTERNATE | WA Order Type | QB Receivables Account | QB Receivables Account ID (QBO only) | Filter for Alternate Mapping (Event Tag) | QB Default Item Product (Inventory List Item) | QB Default Item Product ID (QBO only) | QB Default Income Account | QB Default Class | QB Default Class ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | EventRegistration | Accounts Receivable | 84 | n/a (default mapping) | Events | 19 | Event Revenue | Events | 500000012345 | Undeposited Funds | 4
ALTERNATE | EventRegistration | n/a for alternate | n/a for alternate | Private | Events:Private | 20 | Event Revenue:Private Events | Events | 500000012345 | Undeposited Funds | 4
ALTERNATE | EventRegistration | n/a for alternate | n/a for alternate | Public | Events:Public | 21 | Event Revenue:Public Events | Events | 500000012345 | Undeposited Funds | 4
EXAMPLE: Extra Cost Line Item Exception Mapping |  |  | [use +/- to expand collapse sections]
| WA Type | QB Receivables Account | QB Receivables Account ID (QBO only) | Filter for Line Item Alternate Mapping (Extra Cost Field Name) | QB Default Item Product (Inventory List Item) | QB Default Item Product ID (QBO only) | QB Default Income Account | QB Default Class | QB Default Class ID (QBO only)
| ExtraCost | n/a for extra cost | n/a for extra cost | New Membership Fee | Memberships:New Fee | 20 | Membership Fees:New Fee | Membership | 500000012345
| ExtraCost | n/a for extra cost | n/a for extra cost | T-Shirt | T-Shirts | 21 | Misc Revenue | Membership | 500000012345

## Payment Config
QBWA Mapping Guide - Payment Mapping Config
Use the "+/-" on the left to collapse/expand sections.
NOTES for Payment Configuration: [use +/- to expand collapse sections]
| General | This sheet is focused on the mapping of Payment documents. Payments represent actual payments by credit card, check, or other means. If not linked to another transaction, only default mappings may be used. NOTE: Donation Payments are a special type of transaction that is covered by a different config section.
| Alternate Mappings * | For invoice payments, QBWA attempts to match the payment to the invoice that the payment was settled against. This allows the "linked" invoice to be used to provide alternate mappings for the Deposit To Account if Invoices are in-scope and the mapping is defined. See the Invoice Config sheet for how these values are mapped.
| Definitions | Receivables Account: account where money due from a customer is posted. Deposit-To Account: an account that holds actual funds received (e.g. undeposited funds OR a specific bank account) Tender: The Payment Method.
| Filling out the fields | Use the yellow fields for mapping. Values must match Wild Apricot or Quickbooks exactly. --QB Desktop: Ignore columns that indicate QBO only --QB Online: ID numbers are required. Text account/product/class names are for reference. --If using sub accounts/classes, specify the full string with the colon between levels. (e.g. Membership Income:Membership Fees) Refer to Configuration Guide for more details.
WA Payment Default Mappings: [use +/- to expand collapse sections]
| WA Payment Type | QB Receivables Account | QB Receivables Account ID (QBO only) | QB Payment Deposit-To Account* | QB Payment Deposit-To Account ID* (QBO only)
DEFAULT | InvoicePayment
* See Notes at top of sheet for using "linked" Invoices to map alternate "Deposit-To" accounts for a Payment transaction.
WA Payment Tender Mappings: (also known as Payment Method) [use +/- to expand collapse sections]
| WA Tender Name | QB Tender Name | QB Tender ID (QBO Only)
TENDER | Wild Apricot Payment | Credit Card
TENDER
TENDER
TENDER
TENDER
* insert additional TENDER rows if needed
EXAMPLE: Payment Mapping |  | [use +/- to expand collapse sections]
| WA Payment Type | QB Receivables Account | QB Receivables Account ID (QBO only) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only)
DEFAULT | InvoicePayment | Accounts Receivable | 84 | Undeposited Funds | 4
EXAMPLE: Payment Tender Mapping |  | [use +/- to expand collapse sections]
| WA Tender Name | QB Tender Name | QB Tender ID (QBO Only)
TENDER | Check | Check | 15
TENDER | Credit Card | Credit Card | 26
TENDER | Wild Apricot Payment | Credit Card | 26

## Donation Config
QBWA Mapping Guide - Donation (Payment) Mapping Config
Use the "+/-" on the left to collapse/expand sections.
NOTES for Donation Configuration: [use +/- to expand collapse sections]
| General | This sheet is focused on the mapping of Donation (Payment) documents. Donations are a special type of transaction that is typically not taxable and is not related to an Invoice. To allow mapping of Donation Revenue, a Sales Receipt document is used inside Quickbooks to allow the donation to be allocated to a revenue account and to be placed in the proper "deposit to" account. A default mapping is available for Donations.
| Alternate Mappings | For Donations, a custom "Campaign" field may be used as a means to provide Alternate Mappings to different accounts and classes. Wild Apricot does not proide a Campaign field by default. QBWA assumes a custom field is created for this purpose inside Wild Apricot that has different "single select" choices (drop-down menu items) that represent different campaigns. To use alternate Donation mappings, provide the name of the Donation field below. Consult your Wild Apricot expert r NPC staff if you need assistance creating this field.
| Additional Fields | These fields and formats require configuration for Donations: --Campaign field name: The WA field that is used to specifie Donation Campaigns that may be used to match an alternate QB mapping. --Comment field name: The WA field that allows a customer to add a comment to their donation. This allows QBWA to find that comment and to include it in the QB document created. --Format for QB Comment Format: Any text insertee that clarifies the Comment is from the Donor. At a minimum, use {Comment} to insert the Donor's comment with no additional words. --QB Tax Code for Exempt: For organizations that use Tax, this is needed to tell QB that the transaction is not Taxable. --QBO Tax Code ID for Exempt: The ID for the Tax code above (QBO only). --Use the Payment Tender section of the Payment Config to define the payment methods used for Donations.
| Definitions | Deposit-To Account: an account that holds actual funds received (e.g. undeposited funds OR a specific bank account) Item Product: products or services sold to a customer. (Quickbooks can use this to define default accounts, pricing, etc. for an item. Income Account: account where revenue is posted from sales to customers. Class: Quickbooks allows Classes to be defined for transactions for reporting purposes. Tender: The Payment Method.
| Filling out the fields | Use the yellow fields for mapping. Values must match Wild Apricot or Quickbooks exactly. --QB Desktop: Ignore columns that indicate QBO only --QB Online: ID numbers are required. Text account/product/class names are for reference. --If using sub accounts/classes, specify the full string with the colon between levels. (e.g. Membership Income:Membership Fees) Refer to Configuration Guide for more details.
Donation General Mappings: [use +/- to expand collapse sections]
WA Donation Campaign Field Name: |  |  | e.g. Campaign [The name of the Campaign Field within the WA Donation Form Settings]
WA Donation Comment Field Name: |  |  | e.g. Comment [The name of the Comment Field within the WA Donation Form Settings]
QB Donation Comment Format: |  | {Comment} | e.g. Donor Comment: {Comment} ---> uses your text plus the value of the Comment field on the QB Sales Receipt for the Donation,
QB "Exempt" Tax Code for Donations: |  |  | e.g. E
QBO "Exempt" Tax Code ID for Donations: |  |  | e.g. ##
Payment Tender Mapping: |  | Fill out the Payment Tender mapping on the Payment Config portion of this mapping sheet.
WA Donation (Payment) Mappings: (to create Quickbooks Sales Receipt) [use +/- to expand collapse sections]
<------------------------ DEFAULT mapping is used for Donation if an Alternate mapping is not identified. --------------------------->
DEFAULT or ALTERNATE | Filter for Alternate Mapping (Campaign item from list) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only) | QB Default Item Product (Inventory List Item) | QB Default Item Product ID (QBO only) | QB Default Income Account | QB Default Class | QB Default Class ID (QBO only) | QB Line Description Value
DEFAULT | n/a (default mapping)
ALTERNATE
ALTERNATE
ALTERNATE
ALTERNATE
ALTERNATE
ALTERNATE
ALTERNATE
* insert additional ALTERNATE rows if needed
EXAMPLE: Donation Mapping [use +/- to expand collapse sections]
DEFAULT or ALTERNATE | Filter for Alternate Mapping (Campaign item from list) | QB Payment Deposit-To Account | QB Payment Deposit-To Account ID (QBO only) | QB Default Item Product (Inventory List Item) | QB Default Item Product ID (QBO only) | QB Default Income Account | QB Default Class | QB Default Class ID (QBO only) | QB Line Description Value
DEFAULT | n/a (default mapping) | Undeposited Funds | 4 | Donation | 67 | Donation Income | Donation | 500008343245 | General Donation
ALTERNATE | Capital Expansion | Undeposited Funds | 4 | Donation:Capital | 68 | Donation Income:Capital Campaign | Donation | 500008343245 | Donation to Campaign: {Campaign}
ALTERNATE | Endowment | Undeposited Funds | 4 | Donation:Endowment | 69 | Donation Income:Endowment Campaign | Donation | 500008343245 | Donation to Campaign: {Campaign}
* insert additional ALTERNATE rows if needed

## Sales Tax Config
QBWA Mapping Guide - Sales Taxes Mapping Config
Use the "+/-" on the left to collapse/expand sections.
NOTES for Sales Tax Configuration: [use +/- to expand collapse sections]
| General | This sheet is focused on the mapping of Sales Tax settings between Wild Apricot and Quickbooks. USA and Canada versions of Quickbooks are supported for Online and recent Desktop versions. NOTE: Wild Apricot allows 2 separate taxes to be defined for every transaction line item. There are some combinations of taxation that Quickbooks will not support. QBWA will provide warnings if these combinations are detected.
| Definitions | Sales Tax Account: the QB account used to collect funds that are due to be payable to taxing authorities. Sales Tax Agency Name: the taxing authority to who taxes are payable. Sales Tax Rate: The % added to an invoiced amount as collectable sales taxes. Sales Tax (single): A single tax due to a single taxing authority. Sales Tax Group (multiple): Scenario where multiple authorities are due taxes from the same transaction. Sometimes, these can be redefined as a single tax if one taxing authority collects the tax on behalf of multiple authorities.
| Notes for USA Quickbooks Desktop versions | All non-ID fields are required for allowing the generated-IIF file to be imported to Quickbooks Desktop, however the QB Tax Code is used internal to Quickbooks to define the Tax Rate. If different line items use different tax codes, they will be grouped by lines that use the same tax code. The "Subtotal" List Name must be configured to allow these lines to be grouped and Subtotaled for taxation.
| Notes for USA Quickbooks Online versions | The collected tax amount will be reflected correctly inside Quickbooks. However, the US Online version uses AST (Automated Sales Tax) derivation to determine the appropriate taxation based on buying/selling addreses. This may impact how taxes appear in Quickbooks. Generally, if there are multiple taxing authorities due tax, the collected tax will be split proportionally. Consult Quickbooks help documents for more info.
| Notes for CAN Quickbooks Desktop versions | All non-ID fields are required for allowing the generated-IIF file to be imported to Quickbooks Desktop, however the QB Tax Code is used internal to Quickbooks to define Tax Rates, Accounts, and Taxing Agencies.
| Notes for CAN Quickbooks Online versions | Each line item has a separate tax code that is used internal to Quickbooks to define the appropriate define Tax Rates, Accounts, and Taxing Agencies. Special Case: If your QBO Canada system uses taxes, but you do not collect taxes in WA, configure one record in QBWA with WA Tax ID = NoTaxInWA mapped to the appropriate "zero-rated" or "exempt" QBO tax code.
| Filling out the fields | Use the yellow fields for mapping. Values must match Wild Apricot or Quickbooks exactly. --QB Desktop: Ignore columns that indicate QBO only --QB Online: ID numbers are required. Text account/product/class names are for reference. --If using sub accounts/classes, specify the full string with the colon between levels. (e.g. Membership Income:Membership Fees) Refer to Configuration Guide for more details.
WA Sales Tax Enabled: |  |  | e.g. Yes / No
WA Sales Tax (single) Mappings: [use +/- to expand collapse sections]
| Sales Tax WA Name (reference) | Sales Tax WA ID (required) | Sales Tax QB Code | Sales Tax QBO Code ID (QBO only) | Sales Tax Rate (%) + | Sales Tax QB Account + | Sales Tax QB Agency Name +
* insert additional rows if needed |  |  |  |  | * QBO derives these fields internally based on the QBO Tax Code ID used
QBD Subtotal List Name: |  | Subtotal | e.g. Subtotal [only needed for US Quickbooks Desktop version when different single taces may appear on the same invoice.]
WA Sales Tax Group (multi) Mappings: [use +/- to expand collapse sections]
| Sales Tax Group QB Name | Sales Tax Group QB Code | Sales Tax Group QBO Code ID (QBO only) | Sales Tax Group QB Account | Sales Tax Group QB Agency Name | Component WA Tax ID #1 | Component WA Tax ID #2
* insert additional rows if needed
EXAMPLE: Sales Tax Mappings: [use +/- to expand collapse sections]
| Sales Tax Name | Sales Tax WA ID | Sales Tax QB Code | Sales Tax QBO Code ID (QBO only) | Sales Tax Rate (%) | Sales Tax QB Account | Sales Tax QB Agency Name
| TX Sales Tax | TX-ST | TX State tax | 13 | 6.25 | Sales Tax Payable | Texas State Comptroller
| AUS Sales Tax | AUS-ST | Austin City tax | 14 | 2 | Sales Tax Payable | Texas State Comptroller
| AUS-TX Sales Tax | AUS-TX-ST | Austin | 17 | 8.25 | Sales Tax Payable | Texas State Comptroller
| Exempt |  | E | 2 | 0 | No Tax | No Tax Agency
| GST |  | G | 6 | 5 | Other Current Liability:GST/HST Charged on Sales | Receiver General
| PST |  | P | 9 | 7 | Other Current Liability:PST Payable | Ministry of Finance (BC)
| No Tax Used In WA | NoTaxInWA | Zero-rated | 3 | 0 | Other Current Liability:PST Payable | Ministry of Finance (BC)
EXAMPLE: Sales Tax Group Mappings: [use +/- to expand collapse sections]
| Sales Tax Group QB Name | Sales Tax Group QB Code | Sales Tax Group QBO Code ID (QBO only) | Sales Tax Group QB Account | Sales Tax Group QB Agency Name | Component WA Tax ID #1 | Component WA Tax ID #2
| AUS-TX Group | Austin | 10 | Sales Tax Payable | Texas State Comptroller | TX Sales Tax | AUS Sales Tax | An alternate version of combined tax is shown in the example above. Use one or the other; do not use both.
| Standard GST/PST sales | Sales Tax Group QB Code | 7 | Sales Tax Payable | no tax agency | GST | PST

## Downloaded QBO Accounts
Account ID | Account Name | Full Name | SubAccount | Active | Classification | Account Type | Account SubType | Current Balance | Current balance with SubAccounts | Create Date | Updated Date

## Downloaded QBO Products
QBO Item ID | Item Name | Full Name | Description | Taxable | Income Acct ID | Income Acct Name | Item Type | Parent ID | Parent Name | Active | SubItem | Created | Updated

## Downloaded QBO Classes
Class ID | Class Name | Class Full Name | SubClass | Active | Created | Updated

## Downloaded QBO Payment Methods
Payment Method Name | Payment Method ID | Active | Type

## Downloaded QBO Taxes
Tax Name | Tax Id | Sales Tax Rate List | Tax Group | Taxable | Active | Hidden

## Downloaded WA Member Levels
Member Level ID | Member Level Name | Type | Public Can Apply

## Downloaded WA Tags
Event Tags Used

## Downloaded WA Fields
Field ID | Field Name | Field Instructions | Member Only | Field Type | Type | DisplayType | IsRequired | Access | AdminOnly | IsSystem | SystemCode

## EXAMPLE Scheduled
This sheet provides examples for how QBWA "Scheduled" runs auto-calculate start dates and end dates.
When QBWA scheduling is set to "Manual", the Time Period and Number of Periods settings are ignored.
When QBWA scheduling is set to "Scheduled", the Manual Start Date and Manual End Date are ignored.
| EXAMPLE TIMELINE: | [14 empty] | QBWA RUNS
|  | (in all examples, imagine that today's date is June 14 and QBWA runs today) | [13 empty] | Run Date
| 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21
| 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21
<---- | bar: 2021-05-30 to 2021-06-13
GOAL: Run every 1 month
Scheduling Type = Scheduled
Time Period = Monthly
# of Periods = 1
Weekly-Day of Week = n/a
Monthly-Day of Month = 14
|  | Auto calculated Start Date: |  |  |  |  | Fri, May 14 at 0:00:000 am
|  | Auto calculated End Date: |  |  |  |  | Sun, Jun 13 at 11:59:59 pm
RESULT: QBWA processes all invoices with a date of May 14 through June 13.
GOAL: Run every 2 weeks
Scheduling Type = Scheduled
Time Period = Weekly
# of Periods = 2
Weekly-Day of Week = Mon
Monthly-Day of Month = n/a
|  | Auto calculated Start Date: |  |  |  |  | Mon, May 31 at 0:00:000 am
|  | Auto calculated End Date: |  |  |  |  | Sun, Jun 13 at 11:59:59 pm
RESULT: QBWA processes all invoices with a date of May 31 through June 13.
GOAL: Run every 1 week
Scheduling Type = Scheduled
Time Period = Weekly
# of Periods = 1
Weekly-Day of Week = Mon
Monthly-Day of Month = n/a
|  | Auto calculated Start Date: |  |  |  |  | Mon, Jun 7 at 0:00:000 am
|  | Auto calculated End Date: |  |  |  |  | Sun, Jun 13 at 11:59:59 pm
RESULT: QBWA processes all invoices with a date of June 7 through June 13.
GOAL: Run every 1 day
Scheduling Type = Scheduled
Time Period = Daily
# of Periods = 1
Weekly-Day of Week = n/a
Monthly-Day of Month = n/a
|  | Auto calculated Start Date: |  |  |  |  | Sun, Jun 13 at 0:00:000 am
|  | Auto calculated End Date: |  |  |  |  | Sun, Jun 13 at 11:59:59 pm
RESULT: QBWA processes all invoices with a date of June 13.